## Slide 1: How Quarterly Work Plans are built
November 2017
Nay Pyi Taw

## Slide 2
GLOBAL FUND
MALARIA
TB
HIV/AIDS
Submit
Approved
QWP (Q1)
QWP (Q4)
QWP (Q3)
QWP (Q2)
Implement
PERFORMANCE FRAMEWORK
PSM PLAN
ANNUAL BUDGET
QWP Preparation
Planned activities and procurement accomplished
Achievement of programme targets and goals
Bottom up planning including What, Who, Where, When, How many, How much, Which payment modality

## Slide 3: Development of quarterly work plan
Information from QWP for implementer and FFA to conduct the activity at implementation level
Activity Name
Payment Modality (Direct, Reimbursement, Advance)
Period or Date
S/R/Township/Site (FFA budget allocation, Management by S/R for awareness of all activities)
Planned Budget (Per diem, Travel cost, - for disbursement; training)
Facilitators, Participants, Secretariats (For planning)
Detail Assumptions in the Annual Budget
Budget
Quarterly Work Plan
(as per MCF SOP)
Activity implementation
Report (Variance Explanation)
Travel rates
Food and Lodging fees
Duration of activity
Number of participants (including facilitators)
Form and Report
D1 form/ Technical report
D2 form/ Financial report
Application of lessons learned for future planning (NSP, Annual budgeted WP)
Other Activities (Lab Support, Procurement-IEC/promotional, Maintenance, Renovation, RDS center hiring, outsourcing e.g., warehouse, insurance)
Activity 1 (TRC e.g., Training, Meeting, PSM, M&E, LLIN distribution)- Per diem, TA or travel subsidy or fuel cost, Accommodation, Miscellaneous
Activity 2 (Patient/Provider support: Travel, Incentive/Per diem)
Evaluation and planning meetings at township level with TMO, BHS & IP/ Intensified case detection through mobile clinics
Incentives for ICMV
Renovation

## Slide 4: Preparation and requirement
Information required -
  the activities completion/remaining
  budget (available, expenditure, balance, pipe line expenditure)
  procurement related activities
Activities from budget template are transformed into the work plan format, in excel, and are shared to the participants, prior to the work plan preparation meeting for their inputs, discussion and finalization.
Consolidation of all planned activities by all S/R following the principle of MCF SOP and approved annual budget.
Follow up/ways to expedite pending activities is also discussed during the work plan.

## Slide 5
After compiling the work plan, PR UNOPS team (Programme, MCFU, PSM) review thoroughly the final product assuring that the quarterly work plan as per the MCF SOP and the GF approved budget.
At UNOPS, the 3 diseases work plan are consolidated and conflict schedule for direct disbursement activities are adjusted after consulting the National Programme.
The consolidated QWP is also used for the planning of disbursement by MCFU (amount of cash to be transferred to each FFA.)
Distribution of QWP to the S/R followed by sharing with the township implementing sites is done by National Programme.
Preparation and requirement (Cont’d.,)

## Slide 6: Challenges to be taken care of
During final compilation, too many information needs to be analyzed within limited time
Field level activities are planned separately and when compiling, it sometimes results over planning than the approved budget
Various spelling of Name of townships/hospitals/SDPs required time for data cleaning
Different interpretation of activities leading to planning of activities out of scope
Quarter change – need to remove from previous quarter (to avoid misinterpretation and over/under planning in the following quarters)
Difficult to get real time/updated information on activity completion for reimbursed payment modalities

## Slide 7: Timeline of quarterly work plan
Activities | February/May/ August/November |  |  |  | March/Jun/ September/ December |  |  | 
 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Quarterly work plan template shared to State/Region | X |  |  |  |  |  |  | 
Quarterly work plan meeting held at Central |  | X |  |  |  |  |  | 
Send quarterly work plan draft file to Stage/Region |  |  |  | X |  |  |  | 
Submit quarterly work plan to MoHS |  |  |  |  |  | X |  | 
Quarterly work plan shared to MCFU |  |  |  |  |  | X |  | 
Final quarterly work plan of implementing quarter ready to share to Central and S/R |  |  |  |  |  |  |  | X

## Slide 8
THANK YOU